## Sheet1
Task | T shirt Size | Responsible Person | Due Date | Status | Notes
Create GitHub repo | Small | Michael Wolfe | 2018-12-19 | Done | https://github.com/mjwolfe91/DDS_401_TeamNI_Case_Study1.git
ReadMe file | Small | Michael Wolfe | 2018-12-19 | Done
Introduction (paragraph in Rmd file) | Medium | Michael Wolfe | 2019-01-06 | In Progress
Code - count breweries by state | Medium | Ruben Chavez | 2019-01-06 | Done | remember to clearly annotate before and after code chunk
Code - merge brewery and beer data | Medium | Ruben Chavez | 2019-01-06 | Done | remember to clearly annotate before and after code chunk
Code - count NA's by column | Medium | Ruben Chavez | 2019-01-06 | Done | remember to clearly annotate before and after code chunk
Code - count median alcohol content and IBU by state and plot | Large | Ruben Chavez | 2019-01-06 | Done | remember to clearly annotate before and after code chunk
Code - print states which have largest ABV beer and largest IBU beer | Large | Ruben Chavez | 2019-01-06 | Done | remember to clearly annotate before and after code chunk
Code - summary statistics for ABV variable | Small | Ruben/Michael | 2019-01-06 | Done | remember to clearly annotate before and after code chunk
Code - scatterplot to illustrate relationship between ABV and IBU | Large | Ruben/Michael | 2019-01-06 | Done | remember to clearly annotate before and after code chunk
Merge all Rmd code and smooth out codebook | Large | Michael Wolfe | 2019-01-07 | In Progress
Create PPT to support presentation (might need to split into smaller tasks) | Large | Whole Team | 2019-01-08 | In Progress
Meet to rehearse presentation | Large | Whole Team | 2019-01-08 | In Progress
Turn in and present project | Large | Whole Team | 2019-01-09 | In Progress