## Sheet1
Task | T shirt Size | Responsible Person | Due Date | Notes
Create GitHub repo | Small | Michael Wolfe | 2018-12-19 | I will link this here once I have it set up
ReadMe file | Small | Michael Wolfe | 2018-12-19
Introduction (paragraph in Rmd file) | Medium |  | 2019-01-06
Code - count breweries by state | Medium |  | 2019-01-06 | remember to clearly annotate before and after code chunk
Code - merge brewery and beer data | Medium |  | 2019-01-06 | remember to clearly annotate before and after code chunk
Code - count NA's by column | Medium |  | 2019-01-06 | remember to clearly annotate before and after code chunk
Code - count median alcohol content and IBU by state and plot | Large |  | 2019-01-06 | remember to clearly annotate before and after code chunk
Code - print states which have largest ABV beer and largest IBU beer | Large |  | 2019-01-06 | remember to clearly annotate before and after code chunk
Code - summary statistics for ABV variable | Small |  | 2019-01-06 | remember to clearly annotate before and after code chunk
Code - scatterplot to illustrate relationship between ABV and IBU | Large |  | 2019-01-06 | remember to clearly annotate before and after code chunk
Merge all Rmd code and smooth out codebook | Large | Michael Wolfe | 2019-01-07
Create PPT to support presentation (might need to split into smaller tasks) | Large |  | 2019-01-08
Meet to rehearse presentation | Large | Whole Team | 2019-01-08
Turn in and present project | Large | Whole Team | 2019-01-09